## Sheet1
Gantt Chart and Task Distribution
START DATE | April |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | TIM | ARINDAM | ANOSHAN
| 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31
Preparation
Prepare Research Question | [17 empty] | ✔ | ✔ | ✔ | bar: 2017-04-17
Project Timeline | [17 empty] | ✔ | ✔ | ✔ | bar: 2017-04-17
Research State of the Art | [17 empty] | ✔ | ✔ | ✔ | bar: 2017-04-24
Set Working Time/ GitHub | [17 empty] | ✔ | ✔ | ✔ | bar: 2017-04-24
Model the system
UML/ Class Diagrams | bar: 2017-05-01
Implementing Basic Structure | [17 empty] | ✔ | ✔ | ✔ | bar: 2017-05-01 to 2017-05-15
TEST & REVISE | [17 empty] | ✔ | bar: 2017-05-01 to 2017-05-15
Implementation
Implement the World | bar: 2017-05-15 to 2017-05-22
Implement a Single Car | bar: 2017-05-22 to 2017-05-29
Implement Multiple Car | bar: 2017-05-29 to 2017-06-05
Add in Behaviors | bar: 2017-05-29 to 2017-06-12
Expand the Population | bar: 2017-06-12 to 2017-06-19
Visualization
Test in Qt | bar: 2017-06-19 to 2017-06-26
Project Report
Analysis | bar: 2017-06-26 to 2017-07-03
Writing Up | bar: 2017-07-03 to 2017-07-10
Project Presentation
Presentation | bar: 2017-07-31
| Current Time | [6 empty] | Remarks: - Programming Quiz in mid June - C++ Tutorial is biweekly - Book recommended: Nature of Code - Office Hour Hartanto: Thursday 10:00-11:30 / Struck: ?
Done
To Be Done
Missed
Quiz/ Exams