## Sheet1
START DATE
| April |  |  | May |  |  |  |  | June
| 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19
Expose | bar: 2017-04-17 to 2017-04-24
Prepare research question
Project timeline
Research State of the art
Project structure
Model the system | bar: 2017-05-01 to 2017-05-15
UML-diagrams
Implementation | bar: 2017-05-15 to 2017-05-29
Set up platform
Implement the world
Implement a single car
Test run
Expand the population
Project Report | bar: 2017-05-29 to 2017-06-12
Project Presentation | bar: 2017-06-19